# Information Literacy Action Plan

# A Plan to Implement the IUP Information Literacy Standards

Developed by the IUP Information Literacy Task Force

Plan Outline by Gian Pagnucci

# Year 1 (2000)—Learning Phase—Completed

## Spring, 2000

- Hold Information Literacy Think Tank

# Year 2 (2001-2002)—Planning Phase—Completed

## Fall, 2001

- Provost authorizes funds to develop information literacy at IUP

- Form Information Literacy Task Force

- Research information literacy issues

- Develop IUP Information Literacy Standards

## Spring, 2002

- Collect baseline data on IUP students’ information literacy skills

- Develop Information Literacy Task Force Web Site

- Create R.F.P. for Information Literacy Grants

- Disseminate R.F.P. and IUP Information Literacy Standards

- Create Information Literacy Action Plan

## Summer, 2002

- Award Information Literacy Grants and disburse funds

# Year 3 (2002-2003)—Development Phase

## Fall, 2002

- Hold 2nd Information Literacy Think Tank (town meeting with break-out sessions)

- Have IUP Reflective Practice Project conduct 1-2 information literacy sessions for IUP faculty

- Conduct grant projects

- Provide library assistance to grant winners

## Spring, 2003

- Bring information literacy consultant to IUP

- Hold Information Literacy Grants Showcase (demonstrate course modules)

- Post grant reports on Information Literacy web site

Year 4 (2003-2004)—Implementation Phase

### Curricular Development

#### Through Undergraduate Curriculum Committee

- Begin changing Undergraduate Curriculum proposal process to make information literacy a criteria for all new course/curriculum proposals

##### Through Continuing Education

- Offer non-credit, web-based modules like “Go for the Gold” from James Madison University and others exist on the web, developed by librarians

#### Though Learning Center

#### Incorporate information literacy standards into Learning Center curriculum

#### Through Liberal Studies

- Offer an “Information Literacy” course as an alternative to CO 101 (which counts for Liberal Studies requirements)

- Offer Liberal Studies LS 499: “Information Literacy Synthesis” course (to help students develop their higher order information literacy skills)

#### Through Departmental Majors

- Make information literacy a component or one or more course requirements for all IUP majors

## Faculty Development

- Offer training sessions for faculty (especially of English 202: Research Writing)

- Offer “Information Literacy” course for faculty (1 to 3 credit modules, online, basic and discipline specific)

- Award certificates to faculty for information literacy teaching competence

- Build Learning Communities/Linked Courses around information literacy issues

## Student Development

- Do needs assessment (look at the optimal versus the actual)

- Evaluate what’s being done in individual majors through chair or curriculum committee; assessment both university-wide and by program

- Offer “Information Literacy” course modules, taught by librarians, as an option to discipline courses in majors (1 credit module)

- Encourage more students to take “Learning Strategies” and similar courses offered through the Learning Center

Year 5 (2004-2005)—Standardization Phase

### Curricular Requirements

##### Through All First Year Courses

- Build information literacy component into most first year courses

- Promote student retention through student information literacy skills development

#### Through Undergraduate Curriculum Committee

- Make information literacy a criteria for curriculum proposals going through the Undergraduate Curriculum Committee

#### Through Liberal Studies

- Incorporate IUP Information Literacy Standards into Liberal Studies, either as a proficiency or as a required course

- Offer an approved Liberal Studies elective in Information Literacy as an option/requirement for graduation (1 – 3 credits)

## Faculty Requirements

- Have faculty include information literacy component in most course syllabi

### Student Requirements

### Give all students an Information Literacy Proficiency Exam, offered through IUP Testing Center (online test)

- Require students to take an Information Literacy course if they fail the proficiency exam twice

- Test students on information literacy for admittance to IUP graduate programs